## Sheet1
Task nr | Task name | Duration | Dependencies | Owner | Completed
1. | Incremental Tracking
| - Research and prototyping | 1.5 |  | Dasha | 0%
| - Implementation | 0.5 |  | Dasha | 0%
2. | Fast Camera connection
| - CvCam research | 2 |  | Gordana | 0%
| - implementation | 0.5 |  | Gordana | 0%
3. | INI-File input
| - Implementation | 0.5 |  | Gordana | 0%
4. | Camera calibration
| - Research and prototyping | 2 |  | Veso | 0%
| - Implementation | 0.5 |  | Veso | 0%
5. | Documentation - API and Design specifications
| - Modulizing of the code | 3 |  | Dasha/Veso/Gordana | 0%
| - Classes design | 2 |  | Dasha/Veso/Gordana | 0%
| - API Specification | 1 |  | Dasha/Veso/Gordana | 0%
| - End user documentation | 1 |  | Dasha/Veso/Gordana | 0%
6. | Demo
| - Modifying current project to work with the library | 2 |  | Dasha/Veso/Gordana | 0%
| total duration : | 16.5 |  | total completed : | 0%